## Test Plan
Please click here for Evaly testplan full PDF.

## Mind Maps
Mind Map of Evaly

## TestScenarios
Project Name | Evaly
Reference Document
Created By | Joyanta Shome Akash
Creation Date | 2025-03-02
Approval Date
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 |  | Validate the functionality of "log in" feature | P0 | 21
TS_002 |  | Validate the functionality of "sign up or registration" feature | P0 | 17
TS_003 |  | Validate the "add cart" functionality | P1 | 14
TS_004 |  | Validate the "forgot password" functionality | P1 | 12
TS_005 |  | Validate the "log out" functionality | P2 | 3
TS_006
TS_007
TS_008
TS_009

## TestCase
Product Name |  | Evaly | TC Start Date | 2025-03-03 | TC Execution Start Date | - - | [5 empty] | TEST CASE
Module Name |  | Account | TC End Date | 15/1/2025 | TC Execution End Date | - - |  |  |  |  | PASS | 48
Epic |  |  | Test Case Developed By | Joyanta Shome Akash | Browser (tested) | Yes |  |  |  |  | FAIL | 15
Developer Name (TL) |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | No |  |  |  |  | NO RUN | 5
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 68
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | Account | Browser Compatibility Testing | Account | Checkinging by running the URL site in different browsers | Should be run in different browsers. | Found as per expectation. | Browsers-Chrome, Internet Explorer, Mozilla Firefox, Microsoft Edge, Opera Mini. | 1. Go to different browsers. 2. Search 'evaly' 3. Go to the website. |  |  | Passed
2 | User Authentication |  | Login | verifying that user will not able to login without registration | User should not able to login without registration | Found as per expectation. | chrome | 1. Goto the URL https://evaly.com.bd/ 2. Click on the "sign in" button in the right corner. 3. Enter requirements data 4.Click on "login" button |  |  | Passed
3 |  |  |  | verifying that user will not able to login without registration and showing a error message | when user try to login without reg there should be show a error message | Found as per expectation. | chrome | 1. Goto the URL https://evaly.com.bd/ 2. Click on the "sign in" button in the right corner. 3. Enter requirements data 4.Click on "login" button 5.Error message will show top of the right side |  |  | Passed
4 |  |  |  | verifying that user will able to login with valid credentials and pressing enter key | should be able login successfully pressing enter key | Found as per expectation. | chrome | 1. Goto the URL https://evaly.com.bd/ 2. Click on the "sign in" button in the right corner. 3. Enter requirements data 4.press enter key |  |  | Passed
5 |  |  |  | verifying that user will not able to login without email and password | will not able to login | Found as per expectation. | chrome | 1. Goto the URL https://evaly.com.bd/ 2. Click on the "sign in" button in the right corner. 3. Enter requirements data 4.click login |  |  | Passed
6 |  |  |  | checking when user will try to login without password it should be show password required message in the password field. | Should be show a "password required" message | Found as per expectation. | Chrome, Microsoft edge | 1. Goto the URL https://evaly.com.bd/ 2. Click on the "sign in" button in the right corner. 3. write email on the "enter emial" field 4.click"login" button 4. check "password" field |  |  | Passed
7 |  |  |  | verifying whether an eye icon is addeed to the password field or not | eye icon is added here | Found as per expectation. | Chrome, Microsoft edge | 1. Goto the URL https://evaly.com.bd/ 2. Click on the "sign in" button in the right corner. 3. check password field |  |  | Passed
8 |  |  |  | verifying that eye icon is working when user click to the icon | icon should be worked | Found as per expectation. | Chrome, Microsoft edge | 1. Goto the URL https://evaly.com.bd/ 2. Click on the "sign in" button in the upper right corner. 3. check password field |  |  | Passed
9 |  |  |  | verifying when user will try to login without email it should be show email required message in the email field. | Should be show a "email required" message | Found as per expectation. | Chrome, Microsoft edge | 1. Goto the URL https://evaly.com.bd/ 2. Click on the "sign in" button in the upper right corner. 3. write password on the password field 4.click"login" button 5. check "enter email" field |  |  | Passed
10 |  |  |  | verifying that there is a limit total number of unsuccessful login | should be show a "login failed"message | Found as per expectation. | Chrome, Microsoft edge | 1. Goto the URL https://evaly.com.bd/ 2. Click on the "sign in" button in the right corner. 3. write email on the email field 4.click"login" button 3 times 5.There will show a login failed message in the upper right side |  |  | Passed
11 |  |  |  | verifying logged-in user copies the URL and pastes it into a new browser window, it should redirect to the login page | Should be redirect to the login page | Not found as per expectation. | Chrome, Microsoft edge | 1. Goto the URL https://evaly.com.bd/ 2. Click on the "sign in" button in the upper right corner. 3. Login with valid information 4.copy the loggedin user URL and paste into another browser it's remain same page. | redirect login page error |  | Failed
12 |  |  |  | verifying login user copies the URL and paste it into a new browser window and it automatically log out | Users will be logged out when switching to a new browser | Found as per expectation. | Chrome, Microsoft edge | 1. Goto the URL https://evaly.com.bd/ 2. Click on the "sign in" button in the upper right corner. 3. Login with valid information 4.copy the loggedin user URL and paste into another browser 5.showed login for new browser. |  |  | Passed
13 |  |  |  | checking login by google | Users will be able to log in using Google | Found as per expectation. | Chrome, Microsoft edge | 1. Goto the URL https://evaly.com.bd/ 2. Click on the "sign in" button in the right corner. 3. login by google |  |  | Passed
14 |  |  |  | verifying that when user will go to the login page cursor should remain in the enter email field by default | cursor should be automatically placed in the email field when login page loads | Not found as per expectation. | Chrome, Microsoft edge | 1. Goto the URL https://evaly.com.bd/ 2. Click on the "sign in" button in the right corner. | cursor error |  | Failed
15 |  |  |  | verifying that login with incorrect email and correct password | The system should display an error message | Found as per expectation. | Chrome, Microsoft edge |  |  |  | Passed
16 |  |  |  | verifying that login with correct email and incorrect password | The system should display an error message | Found as per expectation. | Chrome, Microsoft edge |  |  |  | Passed
17 |  |  |  | verifying login with correct credentials but with different letter cases | It should display an error message "Invalid username or password" | Not found as per expectation. | Chrome, Microsoft edge | 1. Goto the URL https://evaly.com.bd/ 2. Click on the "sign in" button in the right corner. 3.enter valid credentials with different letter cases 4.click login | letter cases error |  | Failed
18 |  |  |  | verifying that the user will get into their home page screen after login in with the correct credentials | user will successfully redirect to the home page | Found as per expectation. | Chrome, Microsoft edge |  |  |  | Passed
19 |  |  |  | verifying that user can access all elements and controls by pressing the tab key from the keyboard | user should be able to access all controls using keyboard | Found as per expectation. | Chrome, Microsoft edge |  |  |  | Passed
20 |  |  |  | checking the displayed error message grammar should be corrected | The displayed error message should be grammatically correct. | Found as per expectation. | Chrome, Microsoft edge |  |  |  | Passed
21 |  |  |  | verifying logged in user should not logout on closing the browser | When the user logs in and closes the browser, their session should persist. | Found as per expectation. | Chrome, Microsoft edge |  |  |  | Passed
22 |  |  |  | As the user signs in, on the home page, there is no need for displaying Sign Up or Try Now, etc | should not display sign up or try now | Found as per expectation. |  |  |  |  | Passed
23 |  |  | Logout | verifying successfully logout | user should logout successfully | Found as per expectation. | Chrome,Microsoft edge | 1. after login there will show logout button 2.click logout |  |  | Passed
24 |  |  |  | verifying logout button successfully working | The Log Out button should work properly | Found as per expectation. | Chrome,Microsoft edge | 1. after login there will show logout button 2.click logout |  |  | Passed
25 |  |  |  | verifying logout confirmation | A pop up should appear before logout | Not found as per expectation. | Chrome,Microsoft edge | 1. after login there will show logout button 2.click logout |  |  | Failed
26 |  |  | Registration | verifying that it takes many time to send code number | Code number should be delivered in short time | Not found as per expectation. | Chrome,Microsoft edge | 1. Click Sign up 2.enter full details 3.click create account |  |  | Failed
27 |  |  |  | verifying that resend code button is working or not | resend code should be worked | Found as per expectation. | Chrome,Microsoft edge | 1. Click Sign up 2.enter full details 3.click create account |  |  | Passed
28 |  |  |  | verifying that eye icon for password of create account is working or not | eye icon should be visible | Not found as per expectation. | Chrome,Microsoft edge | 1. Click Sign up 2.enter password |  |  | Failed
29 |  |  |  | verifying that after failed resend code multiple time same email not working it's showing a failed message | should work for that email | Not found as per expectation. | Chrome,Microsoft edge | 1. Click Sign up 2.enter full details 3.click create account |  |  | Failed
30 |  |  |  | verifying that create account button working | should be work create account button | Found as per expectation. | Chrome,Microsoft edge | 1. Click Sign up 2.enter full details 3.click create account |  |  | Passed
31 |  |  |  | verifying by clicking on the eye icon password should be shown for both password and confirm password at the same time | eye icon should be visible for password and confirm password at the same time | Not found as per expectation. | Chrome,Microsoft edge | 1. Click Sign up 2.enter password and confirm password | eye icon error |  | Failed
32 |  |  |  | verifying by clicking on the create account button for blank input | system should display an error message or required fields | Found as per expectation. | Chrome,Microsoft edge | 1. Click Sign up 2.submit form without value |  |  | Passed
33 |  |  |  | verifying that password and confirm password are same or not | should be same | Found as per expectation. | Chrome,Microsoft edge | 1. Click Sign up 2.enter password and confirm password |  |  | Passed
34 |  |  |  | Verify that Attempt to register with an already registered email address. | Should display an error message | Found as per expectation. | Chrome,Microsoft edge | 1. Click Sign up 2.enter all data 3.click create account |  |  | Passed
35 |  |  |  | Password field should have validation for a minimum of 8 to maximum of 16 characters, must contain one special character and have a numerical | The password should be accepted, and the user should be allowed to proceed. | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
36 |  |  |  | Verify example or dummy data shown as placeholder text in the fields. It helps the user to register their account without facing any issues. | The placeholder should be visible when the field is empty. | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
37 |  |  |  | Verify that the user can navigate or access the different controls by pressing the ‘Tab’ key on the keyboard. | user should be able to access all controls using keyboard | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
38 |  |  |  | Verify users can register successfully by entering valid credentials. | user should be successfully registered | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
39 |  |  |  | Verify the system shows an error or not when the email is in an invalid format | Should be show a error message | Not found as per expectation. | Chrome,Microsoft edge | 1. Click Sign up 2.enter invalid email and password 3.click create account | invalid email |  | Failed
40 |  |  |  | Verify that attempting to register with a password that does not meet requirements. | An error message should display that password criteria are not met. | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
41 |  |  |  | verifying that Attempt to register with spaces only in required fields. | An error message should display | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
42 |  |  |  | verifying that Attempt to register with an invalid referral code. | Attempt to register with an invalid referral code. | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
43 | Password Reset |  | Forgot Password | Verifying that the "Forgot Password" button is available on the login page. | The button is visible and clickable. | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
44 |  |  |  | Verifying that clicking the "Forgot Password" link redirects the user to the password recovery page. | The user is taken to the password recovery page. | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
45 |  |  |  | Verify that entering a registered email allows the user to request a password reset. | The system should be send OTP for password reset | Not found as per expectation. | Chrome,Microsoft edge | 1. Click Sign in 2.enter email 3.click forgot password |  | Unable to check. | Not Executed
46 |  |  |  | Verify that entering an unregistered email displays an appropriate error message. | "This email is not registered or user does not exist" message is shown | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
47 |  |  |  | verifying that Attempt to request a password reset without entering an email. | "Forgot Password" option is displayed only after the user enters an email | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
48 |  |  |  | verifying that Attempt to request a password reset using an invalid email format. | System Should be show a error message | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
49 |  |  |  | verifying that Attempt to use an already used password as the new password. | A reset code should be sent to the user's email | Not found as per expectation. | Chrome,Microsoft edge | 1. Click Sign in 2.enter email 3.click forgot password |  | Unable to check. | Not Executed
50 |  |  |  | Verifying that the email field is present on the forget password page to recover the password. | Email field Should be present to the forgot password page | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
51 |  |  |  | verifying Attempt to forgot the password with a weak password. | "Password does not meet security requirements" message is displayed. | Not found as per expectation. | Chrome,Microsoft edge | 1. Click Sign in 2.enter email 3.click forgot password |  | Unable to check. | Not Executed
52 |  |  |  | verifying the whole button should be clickable not only the button text. | whole button should be worked | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
53 |  |  |  | Verifying that the user will get an email after entering a valid email id in forget password. | User Should get an email | Not found as per expectation. | Chrome,Microsoft edge | 1. Click Sign in 2.enter email 3.click forgot password |  | Unable to check. | Not Executed
54 |  |  |  | Verify user should be login successfully with the new password not by the old password. | Should be logged in using new password | Not found as per expectation. | Chrome,Microsoft edge | 1. Click Sign in 2.enter email 3.click forgot password |  | Unable to check. | Not Executed
55 |  |  | Add Cart | verifying whether the Add to Cart button is present or not on the webpage for the product | add cart should be present there | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
56 |  |  |  | verifying user-selected products should be added to the cart page. | product should be add in the cart | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
57 |  |  |  | Verifying Adding the Same Product Multiple Times | The cart should update the quantity of the product instead of adding multiple separate entries | Not found as per expectation. | Chrome,Microsoft edge | 1.Open the Evaly website or app. 2.Search for a specific product. 3.Click on the product and select "Add to Cart." 4.Repeat step 3 multiple times for the same product. 5.Open the cart and check the quantity displayed for the added product. |  |  | Failed
58 |  |  |  | Test users can add more than one item on the cart page | Both Product should be listed in the cart. | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
59 |  |  |  | Cart Behavior When Adding the Same Item Multiple Times and Reloading the Page | The cart should display only one entry for Product A, but with the correct quantity(if added 3 times, quantity should be 3) | Not found as per expectation. | Chrome,Microsoft edge | 1.Open the Evaly website or app. 2.Search for Product A and add it to the cart. 3.Add Product A again (multiple times). 4.Navigate to another page (e.g., Home, Categories, or another Page). 5.Return to the Cart Page. | Quantity_error |  | Failed
60 |  |  |  | Verify the price of the selected product is clearly shown or not on the cart page | price of the product should be clearly visible. | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
61 |  |  |  | Verify total price in front of each product is shown on the webpage or not | The total price for each product should be displayed | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
62 |  |  |  | Verify whether the product delivery charges are mentioned on the cart page or not | The delivery charge should be clearly visible on the cart page. | Not found as per expectation. | Chrome,Microsoft edge | 1.Open the Evaly website or app. 2.Search for Product A and add it to the cart. 3.Navigate to the Cart Page. 4.Look for any mention of delivery charges. |  |  | Failed
63 |  |  |  | Make sure that the expected product delivery time is mentioned on the web page or not | The expected delivery time should be clearly visible. | Not found as per expectation. | Chrome,Microsoft edge | 1.Open the Evaly website or app. 2.Look for any mention of delivery time. |  |  | Failed
64 |  |  |  | Verify whether the user can add multiple products to the cart or not. | All added products should be visible in the cart. | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
65 |  |  |  | Verify user can remove the selected product from the cart successfully or not. | The selected product should be removed from the cart. | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
66 |  |  |  | Verify by adding or removing the same or new product whether the new prices should be updated on the cart page or not. | The cart total price should update dynamically when adding, removing, or changing product quantities. | Found as per expectation. | Chrome,Microsoft edge |  |  |  | Passed
67 |  |  |  | Verify Cart Sync Across Different Browsers | If Evaly uses a user-account-based cart, the previously added product should be visible in Browser B. | Not found as per expectation. | Chrome,Microsoft edge, Evaly App , Safari | 1.Open Browser A and log in to Evaly with a valid account. 2.Add a product to the cart. 3.Open Browser B and log in with the same account. 4.Navigate to the cart page. | cart_error |  | Failed
68 |  |  |  | Verify Cart Reset After Logging into a Different Account | If Evaly uses an account-based cart, the cart should be empty for Account B. | Not found as per expectation. | Chrome,Microsoft edge, Evaly App , Safari | 1.Log in with Account A (Mail 1). 2.Add a product to the cart. 3.Log out of Account A. 4.Log in with Account B (Mail 2) in the same browser. 5.Navigate to the cart page. | different mail cart |  | Failed
Negative test
mmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmm

## Test Summary Report
by
| Test Case Report | [5 empty] | Result :
| Project Name | SecureBank
| Module Name | Account,User authentication,User registration |  |  |  |  | Total No. | Status | New Features:- | Testing Scope:-
| Feature Name | Register Account ,Account Login,Transaction Functionality, Search Functionality
| Test Case Version | 1 |  |  |  |  | 48 | PASS
| Written By | Adrita Alam |  |  |  |  | 15 | FAIL
| Executed By | Adrita Alam |  |  |  |  | 5 | Not Executed
| Reviewed By | Ehsanul Alam Sabbir |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Testing Environment : Google Chrome Browser
| Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
|  | 48 | 15 | 5 | 0 | 68
| Grand Total | 48 | 15 | 5 | 0 | 68
LIMITATIONS
| Documents |  |  |  | Received | Useful
| PRD |  |  |  | No | No
| USER STORY |  |  |  | No | No
|  | Testing Type in Scope | Description
| Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
| Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
| Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
| Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
| Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
| Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
| Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting | Bug Reporting
#SL 01 | #SL 07
Issue: Logged-in User Can Access Restricted Pages by Copy-Pasting URL in a New Browser Window | Issue: After Multiple Failed Resend Attempts, Same Email No Longer Works and Shows a Failed
Reproducing Steps: | Reproducing Steps:
1. Goto the URL https://evaly.com.bd/ | 1. Click Sign up
2. Click on the "sign in" button in the upper right corner. | 2.enter full details
3. Login with valid information | 3.click create account
4.copy the loggedin user URL and paste into another browser it's remain same page.
Env: | Env:
Module: Login | Module: Registration
Priority: P2 | Priority: P0
Severity: Minor | Severity: Major
Screenshot: redirect login page error | Screenshot: redirect login page error
Expected: The system should detect that the user is not authenticated and redirect them to the login page. | Expected: The same email should continue working after waiting
Responsible QA: Joyanta Shome Akash | Responsible QA: Joyanta Shome Akash
Bug Reporting | Bug Reporting
#SL 02 | #SL 08
Issue: Curson was not in enter email textbox | Issue: Eye icon was not showing for password and confirm password
Reproducing Steps: | Reproducing Steps:
1. Goto the URL https://evaly.com.bd/ | 1. Click Sign up
2. Click on the "sign in" button in the right corner. | 2. Enter password and confirm password
Env: | Env:
Module: Login | Module: Registration
Priority: P3 | Priority: P3
Severity: Minor | Severity: Minor
Screenshot: Cursor_error | Screenshot: Eye Icon
Expected: cursor should be automatically placed in the email field when login page loads | Expected: Clicking the eye icon should toggle visibility for both the "Password" and "Confirm Password" fields at the same time.
Responsible QA: Joyanta Shome Akash | Responsible QA: Joyanta Shome Akash
Bug Reporting | Bug Reporting
#SL 03 | #SL 09
Issue: login with correct credentials but with different letter cases and it logged in | Issue: System does not show an error for an invalid email format
Reproducing Steps: | Reproducing Steps:
1.Goto the URL https://evaly.com.bd/ | 1. Click Sign up
2. Click on the "sign in" button in the right corner. | 2.enter invalid email and password
3. Enter valid credentials with different letter cases | 3.click create account
4. click login
Env: | Env:
Module: login | Module: Registration
Priority: P0 | Priority: P1
Severity: Major | Severity: Major
Screenshot: letter case error | Screenshot: invalid email error
Expected: It should display an error message "Invalid username or password" | Expected: It should display an error message "Invalid Email"
Responsible QA: Joyanta Shome Akash | Responsible QA: Joyanta Shome Akash
Bug Reporting
#SL 04 | #SL 10
Issue: No logout confirmation | Issue:
Reproducing Steps: | Reproducing Steps:
1. after login there will show logout button
2.click logout
Env: | Env:
Module: logout | Module:
Priority: P3 | Priority: P3
Severity: Minor | Severity: Minor
Screenshot: | Screenshot:
Expected: A pop up should appear before logout | Expected: A pop up should appear before logout
Responsible QA: Joyanta shome Akash | Responsible QA: Joyanta shome Akash
Bug Reporting
#SL 05
Issue: Verification Code Delivery Takes Too Long
Reproducing Steps:
1. Click Sign up
2. enter full details
3. click create account
Env:
Module: Registration
Priority: P1
Severity: Major
Screenshot:
Expected: The verification code should arrive within 30 seconds or less
Responsible QA: Joyanta Shome Akash
Bug Reporting | Bug Reporting
#SL 06
Issue: Eye Icon for Password Visibility in Create Account Page Not Functioning Properly
Reproducing Steps:
1.Click Signup
2.enter password
Env:
Module: Registration
Priority: P3
Severity: Minor
Screenshot: eye icon
Expected: The password should visible text when clicking the eye icon
Responsible QA: Joyanta Shome Akash

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (63/68)*100 = 92.64
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (5/68)*100 = 7.35
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (48/63)*100 = 76.19%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (15/63)*100 = 23.08%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/63)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A